## Project Schedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Project Two
Enter Company Name in cell B2. | Complete this template by replacing the bracketed text with the relevant information in each row. Also, in the relevant columns, be sure to enter start and end dates and experiment with entering progress percentages to create the Gantt chart bars.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  |  | 2026-03-01
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  | 1 |  |  | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2026-03-02 to 2026-04-26
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | PROGRESS | START | END | DAYS | time axis 2026-03-02 to 2026-04-26
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Phase 1: Security Assessment and Initial Planning | 10% | 2026-02-09 | 2026-02-22 | 14
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Evaluate employee awareness of cybersecurity practices | 25% | 2026-02-09 | 2026-02-13 | 5
| Analyze current patch management workflow and gaps | 10% | 2026-02-09 | 2026-02-16 | 8
| Review existing firewall configuration and security infrastructure | 0% | 2026-02-10 | 2026-02-20 | 11
| Milestone: Security Assessment Complete |  |  | 2026-02-22
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Phase 2: Policy Development and Process Improvement | 0% | 2026-02-23 | 2026-03-15 | 21
| Develop updated patch management standards and schedule | 0% | 2026-02-23 | 2026-03-05 | 11
| Create stronger authentication and password policy requirements | 0% | 2026-02-24 | 2026-03-08
| Assess and revise backup and disaster recovery procedures | 0% | 2026-02-25 | 2026-03-12 | 16
| Milestone: Policies Approved |  |  | 2026-03-15
| Phase 3: Security Technology Deployment | 0% | 2026-03-16 | 2026-04-15
| Deploy next-generation firewall solution | 0% | 2026-03-16 | 2026-04-05 | 21
| Implement updated endpoint protection tools across the network | 0% | 2026-03-18 | 2026-04-08 | 22
| Establish centralized monitoring and threat alert configuration | 0% | 2026-03-20 | 2026-04-15 | 27
| Milestone: Infrastructure Hardened |  |  | 2026-04-15
| Phase 3A: Document Conversion Implementation | 0% | 2026-03-10 | 2026-04-20
| Identify document conversion requirements | 0% | 2026-03-10 | 2026-03-14
| Contract database administrator (DBA) | 0% | 2026-03-12 | 2026-03-18
| Install document conversion software | 0% | 2026-03-20 | 2026-04-02
| Integrate PDF generation into reporting systems | 0% | 2026-04-03 | 2026-04-15
| Test data integrity and file conversion process | 0% | 2026-04-16 | 2026-04-20
| Milestone: Document Conversion Implementation Complete |  |  | 2026-04-20
| Phase 4: Workforce Training and Security Validation | 0% | 2026-04-13 | 2026-05-24
| Deliver employee cybersecurity awareness training sessions | 0% | 2026-04-13 | 2026-05-01
| Conduct vulnerability scanning and penetration testing activities | 0% | 2026-04-20 | 2026-05-15
| Perform final evaluation of security controls and risk reduction | 0% | 2026-05-02 | 2026-05-20 | 19
| Milestone: Workforce Training Complete |  |  | 2026-05-24
Adapted from a template by TeamGantt (2019), https://www.teamgantt.com/

## Resource Allocation
Complete this template by entering the relevant information in each row.
Task | Resource | Rationale
Evaluate employee awareness of cybersecurity practices | Project Manager | The project manager coordinates communication across departments and gathers input to identify employee knowledge gaps.
Analyze current patch management workflow and gaps | Software Engineers Team Lead | Patch management is software-driven and requires technical expertise to evaluate update cycles and vulnerabilities.
Review existing firewall configuration and security infrastructure | Hardware Engineers Team Lead | Firewall and infrastructure assessments require knowledge of network hardware and architecture.
Develop updated patch management standards and schedule | Software Engineers Team Lead | This task involves system updates and configuration planning aligned with software engineering responsibilities.
Create stronger authentication and password policy requirements | Project Manager | Policy creation requires coordination across teams and alignment with organizational security goals.
Assess and revise backup and disaster recovery procedures | Software Engineers Team Lead | Backup and recovery systems rely on software tools and require technical configuration and evaluation.
Deploy next-generation firewall solution | Hardware Engineers Team Lead + Contractor | Hardware engineers manage configuration while the contractor supports physical setup and installation.
Implement updated endpoint protection tools across the network | Software Engineers Team Lead | Endpoint protection deployment and monitoring rely on software configuration expertise.
Establish centralized monitoring and threat alert configuration | Software Engineers Team Lead | Monitoring systems require integration and configuration of security software tools.
Deliver employee cybersecurity awareness training sessions | Project Manager + Contractor | The project manager organizes the sessions while the contractor assists with logistics and setup.
Conduct vulnerability scanning and penetration testing activities | Software Engineers Team Lead + Hardware Engineers Team Lead | Both software and infrastructure expertise are required to identify and test vulnerabilities across systems.
Perform final evaluation of security controls and risk reduction | Project Manager | The project manager reviews outcomes, ensures goals were met, and reports results to stakeholders.
Project milestone reviews and approvals | Stakeholders | Stakeholders provide oversight, funding approval, and decision-making at key checkpoints.
Final project sign-off and closure | Stakeholders + Project Manager | Stakeholders approve completion while the project manager finalizes documentation and project delivery.